## Introduction
UAT Template Example User Acceptance Testing (UAT) Planning Document
Developer: | FY23 SLDS Scalable Data Use Workgroup
Version: | 1
Release Date: | 2024-09-18
GitHub: | https://github.com/CEDS-Collaborative-Exchange
Description:
An example usage of the User Acceptance Testing template completed alongside software posted on the CEDS Collaborative Exchange.
Companion Documents:
UAT Best Practices
UAT Template

## Example
Evaluation of TEST Environment Readiness for CEDS Installation User Acceptance Testing (UAT) Planning Document
Developer: | CEDS Implementation team
Version: | 1
Release Date: | 2025-01-01
GitHub: | https://github.com/CEDS-Collaborative-Exchange
1. INTRODUCTION
Scope: | The scope of this UAT evaluation is to verify readiness of the test environment for the CEDS implementation, ensuring that users are able to log into the environment and successfully navigate without errors.
Approach: | Testers will use the Sections 6, 7 and 8 below to verify functionality, usability, performance and validate compliance.
Resources: | Network & Security, Systems team, and Testing team.
Schedule: | Testing will commence on 01/06/25 and testing duration will be three (3) days
Execution: | Testers will follow Section 6.2 test cases, using Section 6.3 test data, and completing Section 8 to report identified defects.
2. UAT OBJECTIVES
2.1 General Objectives
Verify that the software solution meets the agreed business requirements.
Identify and resolve any defects or issues before deployment.
Ensure that the system performs as expected in real-world scenarios.
Gain formal approval from stakeholders to proceed to production.
2.2 Specific Objectives
As outlined in Section 6.2 test cases
3. UAT APPROACH
3.1 Testing Types
Functional Testing: | Ensure that users are able to log in and navigate the system without error.
Usability Testing: | Evaluate TEST system's behavior to ensure login is error free
Performance Testing: | Evaluation of TEST system's responsiveness and stability
Regression Testing: | Login issues identified in defects section remediated and retested.
3.2 Test Environment
Testing to be performed on personal computer with the issued versions of SQL and Power BI.
4. ROLES AND RESPONSIBILITIES
Role: |  | Count: | Personnel:
Project Manager: |  | 1 | Lauren Baker
UAT Manager: |  | 1 | Angela Rampling
Business Analyst: |  | 2 | Charles Ince, Pippa Ince
Developer: |  | 1 | Elizabeth Clark
Tester: |  | 2 | Tim Nash, Abigail Cameron
5. USE CASE
The software has the capability to lift suppression for authorized users. This should be thoroughly tested to prevent the exposure of protected data.
6. TEST PLAN
6.1 Test Plan Definition
Evaluation of TEST environment readiness: develop a list of all test cases; execute all test cases, track defects, analyze results; confirm user acceptance by reviewing test results; documentation of test results; obtain UAT sign-off
6.2 Test Cases
https://infoshare.myuniversity.edu/TechDocs/
6.3 Test Data
https://infoshare.myuniversity.edu/TechDocs/
6.4 Test Schedule
Testing will commence on 1/06/25 and testing duration and remediation will be for three (3) days.
7. ENTRY AND EXIT CRITERIA
7.1 Entry Criteria
Test cases developed and approved; test data prepared, test execution completed, test results and metrics recorded.
7.2 Exit Criteria
Test execution completed and all planned tests have been run at least once, defects logged, test results and metrics recorded.
8. DEFECT MANAGEMENT
8.1 Defect Reporting
Invalid network Login + https://infoshare.myuniversity.edu/TechDocs/DefectReporting/
8.2 Defect Triage
Ensure that network connectivity is properly configured; verified that user account and permissions are set up in TEST as required; coordinate with end-user to re-test to ensure issue is resolved.
9. RISKS AND MITIGATIONS
Review the project scope and objectives to understand the potential risks - execute each test case one by one and document results observed. If any defects or issues are identified, report them promptly and re-test the fixed defects to ensure they have been resolved.
10. SIGN-OFF
Review test results and compare with expected outcomes, documenting findings or concerns. Provide feedback and recomendations for improvement if necessary, Discuss findings with stakeholders and make a decision regarding user acceptance of the system based on test results and discussions.